## Form Responses 1
Timestamp | Untitled Question

## Project Timeline
Team Graceful
TIMELINE
PROJECT DETAILS
DATE | MILESTONE | POSITION | BASELINE
2016-08-31 | Project Start | -5 | 1
2016-09-07 | Team Meeting; 1st homework started | 5 | 1
2016-09-14 | Team status report | 10 | 1
2016-09-21 | Homework #2 Due | 15 | 1
2016-09-28 | Homework #3 Due | 20 | 1
2016-10-05 | UML diags final; proj plan final | 5 | 1
2016-10-12 | Database design draft | 10 | 1
2016-10-19 | Mid-semester peer reviews due | 15 | 1
2016-10-26 | Draft IT requirements, including network design | 5 | 1
2016-11-02 | Homework #4 Due | 10 | 1
2016-11-09 | First Demo of Prototype | -5 | 1
2016-11-16 | User Validation & Test plan finalized | 10 | 1
2016-11-23 | Client Visit | -5 | 1
2016-11-30 | Draft Documentation | 5 | 1
2016-12-07 | Paper Due - Final Documentation | 10 | 1
2016-12-14 | FINAL PRESENTATION! | -5 | 1
Project Timeline Tips:
The role of the Position values in the Project Details table is to prevent the Milestone labels from overlapping each other on the timeline. Use positive numbers to position labels above the timeline and negative numbers to position them below.
To add additional Milestones, either insert new rows within the table or start typing below the last table entry and the table will automatically expand to accommodate your newly added data.
Project Start
Design Network

## Project Plan Details
Date | Milestone | Tasks | Responsible | Notes
2015-08-31 | Project Start | Form team: make introductions; inventory skill strengths and weaknesses; forumulate and document initial roles and responsibilities (to be modified as needed later). | All
2015-08-31 | Project Start | Schedule 1st team meeting - and attempt to choose recurring team meeting times that work for everyone (can be established later); establish a communications plan (ie. share emails, cell#'s, and establish how you will stay in touch) | All
2015-08-31 | Project Start | Further develop this project plan (it is part of HW1) - THINK through your time management and what you will accomplish as the weeks progress. | All
2015-09-07 | Team Meeting; 1st homework started | Have met at least once by the end of the day on 9/7; have started Homework #1 minimally - add more items to this project plan in the empty lines below and have altered this line to be something more meaninful than my babble… | All
| fill me in… | fill me in…
| fill me in… | fill me in…
2015-09-14 | Homework #1 Due! | Have met at least twice - this is your last reminder from me in this template that you need to meet regularly outside of class - if you are not, you will not do well in this class; Have HW1 done; Have this project plan completely filled in for review and comments back so you will know if you have a good plan to get to end-game; Have your client questionnaire finalized and be prepared to interview the client. | All
| fill me in… | fill me in…
| fill me in… | fill me in…
2015-09-21 | Homework #2 Due | E-R diagrams complete with supporting documentation if explanation is required for anything you document in your diagrams.
| fill me in… | fill me in…
| fill me in… | fill me in…
2015-09-28 | Homework #3 Due | Complete mock-ups (ie. wireframes) of your user interface.
| fill me in… | fill me in…
| fill me in… | fill me in…
2015-10-05 | UML diags final; proj plan final | Final Project Plan - updated with all input from instructor Final UML Diagrams
| fill me in… | fill me in…
| fill me in… | fill me in…
2015-10-12 | Database design draft | Draft database design
| fill me in… | fill me in…
| fill me in… | fill me in…
2015-10-19 | Mid-semester peer reviews due | Complete initial (ie. first pass feedback) peer reviews
| fill me in… | fill me in…
| fill me in… | fill me in…
2015-10-26 | Draft IT requirements, including network design
| fill me in… | fill me in…
| fill me in… | fill me in…
2015-11-02 | Homework #4 Due | Database prototype complete
2015-11-09 | First Demo of Prototype | Complete project prototype first-pass demo ready
2015-11-16 | User Validation & Test plan finalized | Test plan for all aspects of the prototype complete User validation tests to be performed by client documented
2015-11-23 | Client Visit | Updates to user validation complete (as required) One key question to ask the client dcoumented
2015-11-30 | Draft Documentation | All documentation required for the project in Draft form
2015-12-07 | Paper Due - Final Documentation | All documentation required for the project in FINAL form
2015-12-07 | Final Peer Evaluations | Complete final peer evaluation forms and submit | All
2015-12-14 | FINAL PRESENTATION! | Git er dun! | All

## Week Class Sched - Fall2015
Week | Class Topics and Activities | Assignments Due | Class Format
8/31 | Introduction; Project case study; Project plan; |  | Group (HC2023)
Sections and Teams; Project overview
9/7 | NO CLASS: Labor Day
9/14 | Client Interview | Homework 1 due | Group (HC2023)
9/21 | SME visit | Team status report
Brown bag session
Homework 2 due
9/28 | Project Management and UML | Team status report | Group (HC2023)
Brown bag session
Homework 3 due
10/5 | Guest presentation: Alan Labouseur - database | Team status report | Group (HC2023)
Brown bag session
10/12 |  | Team status report | HC2023 available
|  | Brown bag session | if needed
10/19 | Networking | Team status report | Group (HC2023)
| Draft peer-reviews | Brown bag session
10/26 |  | Team status report
Brown bag session
11/2 |  | Team status report: Database | HC2023 available
|  | Homework 4 due | if needed
11/9 | Prototype 1st Demonstration | Rough draft demo presentations
11/16 | User Validation & Test Planning | Team status report | Group (HC2023)
Brown bag session
11/23 | Client visit | Team status report
Brown bag session
11/30 | SME visit | Team status report
| Draft documentation / paper | Brown bag session
12/7 | Final documentation / paper | Brown bag session
| Final peer-reviews | Project paper due
Peer evaluations due
12/14 | Project presentations | Project prototype due
Project presentations

## Weekly Status Reports
Status Report - Team name, members
Date
RGY | Item | Description | Mitigation / Help needed
Red
Yellow
Green