## Form Responses 1
Timestamp | Untitled Question

## Project Timeline
Team Graceful
TIMELINE
PROJECT DETAILS
DATE | MILESTONE | POSITION | BASELINE
2016-08-31 | Project Start | -5 | 1
2016-09-07 | Team Meeting; 1st homework started | 5 | 1
2016-09-14 | Team status report | 10 | 1
2016-09-21 | Topology Diagram/Design Network/Server | 15 | 1
2016-09-28 | DNS Design/Gain access to CPCA website | 20 | 1
Portal for Facilitators/Referals
2016-10-05 | Technology Documentation | 5 | 1
Network implementation/design database
2016-10-12 | Server implementation/Redesign website | 10 | 1
2016-10-19 | Application authentication and implementation | 15 | 1
2016-10-26 | Draft IT requirements, including network design | 5 | 1
2016-11-02 | Save VM's and give to Dev team | 10 | 1
Mobile friendly site given time
2016-11-09 | First Demo of Prototype | -5 | 1
2016-11-16 | User Validation & Test plan finalized | 10 | 1
2016-11-23 | Client Visit | -5 | 1
2016-11-30 | Draft Documentation | 5 | 1
2016-12-07 | Paper Due - Final Documentation | 10 | 1
2016-12-14 | FINAL PRESENTATION! | -5 | 1
Project Start
Design Network/ IT Requirements
Implement Server
Team Meeting:1st Homework
Team Status Report
Topology Diagram
Website and Portal
Technology Documentation
Application Authentication
Save VM’s/ Website
Demo Prototype
Test Plan
Client Visit
Draft Documentation
Final Documentation Due
Final Presentation

## Project Plan Details
Date | Milestone | Tasks | Responsible | Notes
2016-08-31 | Project Start | Form team: make introductions; inventory skill strengths and weaknesses; forumulate and document initial roles and responsibilities (to be modified as needed later). | All
2015-08-31 | Project Start | Schedule 1st team meeting - and attempt to choose recurring team meeting times that work for everyone (can be established later); establish a communications plan (ie. share emails, cell#'s, and establish how you will stay in touch) | All
2015-08-31 | Project Start | Further develop this project plan (it is part of HW1) - THINK through your time management and what you will accomplish as the weeks progress. | All
2015-09-07 | Team Meeting; 1st homework started | Have met at least once by the end of the day on 9/7; have started Homework #1 | All
2016-09-09 | Team Meeting: 2nd Came up with a project and created Req doc | The first time our team met we decided on what we want to do for the project and created a requirements doc. We then filled out the parts that we were responsible for in the doc and set a date to me again for the timeline and status report. | All
2016-09-14 | Team Meeting 3rd; Finished project plan and set a time to meet for next time. | The second time we met we worked on the project plan and divided up all of the work for everybody to do. We also planned the next time we were going to meet. | All
2016-09-21 | Homework #1 Due! | Have HW1 done; Have this project plan completely filled in for review and comments back so you will know if you have a good plan to get to end-game; Have your client questionnaire finalized and be prepared to interview the client. | All
2016-10-03 | Team Meeting 4th; | Split workload into two groups. Three of us mapped out the ER diagram, while the others worked on the Use-Case Diagram | All
2016-10-05 | Team Meeting 5th; | Finishing up E/R diagrams, Use-Case Diagrams, and updating Project plans and Team status reports. Opened a document for wireframe. | All
2016-10-05 | Homework #2 Due | E-R diagrams complete. Use-Case diagrams completed. Project plan completed. Team Status Report completed. | All
2016-10-05 | Class Meeting | Establish roles,
| Team Meeting 6th; | Split up work, Send Chris DiDona revisions to project plan, Finalize individual team's plans, work on wireframes. Team status reports | All
| Team Meeting 7th; | fill me in…
2016-10-10 | Team meeting #7: Rough draft test plan | Created a rough draft test plan to test the database, GUI and intake packet.
2016-10-12 | Homework #3 Due | Complete a rough draft test plan of the database, GUI and intake packet. | All
| fill me in… | fill me in…
| fill me in… | fill me in…
| fill me in… | fill me in…
| fill me in… | fill me in…
2015-10-17 | Team meeting #8: Test plan rough draft Algozzine updates | Update test plan and add the feedback that Algozzine gave. Add two addtional tables as well and come up with testing for them as well. | All
| fill me in… | fill me in…
| fill me in… | fill me in…
2016-10-19 | UML diags final; proj plan final | Final Project Plan - updated with all input from instructor Final UML Diagrams and updated test plan. | All
| fill me in… | fill me in…
| fill me in… | fill me in…
2016-10-24 | Team meeting #9: Second round of feedback | Make updates again from the feeback that Algozzine left on the test plan. This will be our second revision. | All
| fill me in… | fill me in…
| fill me in… | fill me in…
2016-11-02 |  |  | All
| First Demo of Prototype | Complete project prototype first-pass demo ready | All
| User Validation & Test plan finalized | Test plan for all aspects of the prototype complete User validation tests to be performed by client documented | All
| Client Visit | Updates to user validation complete (as required) One key question to ask the client dcoumented | All
| Draft Documentation | All documentation required for the project in Draft form | All
| Paper Due - Final Documentation | All documentation required for the project in FINAL form | All
| Final Peer Evaluations | Complete final peer evaluation forms and submit | All
| FINAL PRESENTATION! | Git er dun! | All

## Weekly Status Reports
Status Report - Team Graceful, Sacha, Grace, Colby, Bradley, Cameron
Date
RGY | Item | Description | Mitigation / Help needed
Red | None at this time.
Yellow | Database, the form filable PDF, and the GUI. | All are being worked on at this time and are in the process of sucessfully finishing within a timly manor in order to start the testing upon. | If they are not finished in a timly manor then, reduced scope for the rest of the project must be considered.
Green | Finalized project plan, E/r diagram, and Use-Case diagram are finished. Pre-finalized Test plan is finished. Test team is ready to begin testing on the database and intake form. | Finished E/R, Use-Case, and updated project plan | As of right now, we do not need help to complete this assignment on time.

## Week Class Sched - Fall2016
Week | Class Topics and Activities | Assignments Due
8/31 | Introduction; Project case study; Project plan; | n/a
Sections and Teams; Project overview
9/7 | Client Interview - Requirements gathering | Prepared Questions for client interview
Completed CBL Pre-Survey
9/14 | SME visit - UML diagramming | Homework 2 due including: Team Status report
| Dr. Carolyn Matheus | Project Plan, Team Status Report, CBL Forum
9/21 | Project Management and UML | Homework 2 due including: Team Status report
Updated Project Plan, Use Case Diagrams,
Finalized Req Doc, E/R diagram
9/28 | Guest presentation: Alan Labouseur - database | Homework 3including: Team status report
Finalized Project Plan, Wireframes, CBL forum
10/5 | 3 way split - IT/IS/CS in seperate rooms | Team status report
10/12 | SME visit - Database review & debugging | Team status report&Finalized E/R diagrams
| Dr. ALan Labouseur, Dr. Pablo Rivas | Early demo of database if possible
10/19 | Group work in class | Team status report
10/26 | Group work in class | Team status report
CBL Forum
11/2 | Group work in class | Team status report
Demo of databases for grade
11/9 | Group work in class | Team status report
Demo of User Interface for grade
11/16 | Group work in class | Team status report
CBL forum
11/23 | NO CLASS
11/30 | Group work in class | Team status report
12/7 | Final status, hand in all documentation | Team status report
| Fine tuning of demo | Project Paper due(documentation)
| Expectations for final presentations | Peer evaluations due
CBL post-survey
2016-12-14 | Project presentations | Project prototype due
Project presentations