## Sheet1
Req # | Description | Source | Priority | Notes
1 | Design network | IT team | H | How many locations will there be, use of IPv4 and IPv6, routing protocols, security
2 | design server | IT team | H | operating system, servers
3 | DNS design | IT team | H | create namespace for devices, servers, and hosts
4 | Topology Diagram | IT team | H | make a regular one, one for layer 2, and one for IPv4 addressing scheme
5 | Technology Documentation | IT team | H | for each protocol or feature or technology that will be used, a brief paragraph will be written
7 | Network Implementation | IT team | M | Create network topolgy scheme in CISCO or other mock up software. Recreate the the netowrk in simulation software to test functionality of system.
8 | Portal for Facilitators/Referals | CS team | H | Log in? Pictures of students, Class progress completion, Facilitators able to take notes on portal.
9.1 | Gaining access to the CPCA website | CS team | H | Needs a link to some sort of log-in system.
9.2 | Redesign CPCA website | CS team | L | Depending on timeframe/completion, website rework?
9.3 | Mobile Friendly Site | CS team | M | Mobile friendly site to access from Smart phones
10 | Design a database | CS team | H | Implement a database. Language? Application?
11 | Server Implementation in VM Envi. | IT team | M | Create VMs in a virtual enviroment, install and config OS, and create backup of the VM system. Do this for all servers, but create new VMs for each one.
12 | Application Authentication & Implementation | IT team | M | Implement Centralized Authentication Service.
13 | Save the VM's & give them to Dev team | IT team | L | Once our VM's are complete they will be saved and given to dev team for testing their software.
14 | Testing and Verifying | IT team | H | Testing our network and server setup, as well as the dev teams software. Make sure that all technologys and software is compatible within the system.
13 | Extensibility of the system | Professor | H | We will not implement everything this semester, so making something that can easily be extended is key